## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
A. Milestone: Tablet Device | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1A. Research software data for restaurant tablets | What brand works best for our POS? | 2023-01-01 | 2023-06-01 | 5 days | Seyou | bar: WEEK 1 M 1 to WEEK 2 M 6
2A.Compare tablet pricing |  |  |  | 5
3A.Compatible OS system for current POS integration |  |  |  | 4
4A.Map out POS diagram for bar area in all locations | Make sure plugs are okay for proposed areas | 2023-01-13 | 2023-01-16 | 1 | Deanna, Seyou, Peta, Location Mgr.s | bar: WEEK 3 W 13 to WEEK 4 M 16
5A.Electrician installing bar tablets first | Will all devices be docked with a plug in? | 2023-01-16 | 2023-01-19 | 2 | Seyou, Peta | bar: WEEK 4 M 16 to WEEK 4 R 19
6A. Should POS be set for QR code access from customers phone as an alternative? | Should this be QR access only? | 2023-01-20 | 2023-01-22 | 1 | Deanna, Seyou, Peta, Location Mgr.s | bar: WEEK 4 F 20 to WEEK 5 T 22
7A. No tipping feature installed on POS - staff input |  |  |  | 1
8A. Drilldown 'no tipping' aspects on POS system |  |  |  | 1
9A. Test software on tablets | Does it integrate with current POS for ordering? | 2023-01-20 | 2023-01-22 | 1 | Seyou, Peta, Location Mgrs. | bar: WEEK 4 F 20 to WEEK 5 T 22
10A. Approve tablet marketing wraps to match menu style/look | Does the tablet work with overall look? | 2023-01-06 | 2023-01-10 | 1 | Deanna, Gilly, Alex, Peta
11A. Align and evaluate stakeholders | Confirm tablet look as wanted? | 2023-01-11 | 2023-01-14 | 1 | Omar, Deanna, Seyou, Peta | bar: WEEK 3 M 11 to WEEK 3 W 13
B. Milestone: Training and troubleshooting
1B. Project Plan Updates |  | 2023-01-06 | 2023-01-10 | 1 | bar: WEEK 3 M 11 to WEEK 3 W 13
2B. Locations hold small update project meeting about tablet launch |  | 2023-01-13 | 2023-01-16 | 1 | bar: WEEK 3 W 13 to WEEK 4 M 16
3B. Create troubleshoot/support plan for all locations | What to do when things get crazy? | 2023-01-23 | 2023-01-25 | 2 | Seyou, Peta, Deanna, Location Mgrs. | bar: WEEK 5 W 23 to WEEK 5 F 25
4B. Create training modules for employees to learn | Easy to learn? | 2023-01-23 | 1900-01-23 | 2 days | Kitchen Staff, Carter, Location Mgrs. | bar: WEEK 5 W 23 to WEEK 5 R 24
5B. Train GM's on new software | Comfortable enough to troubleshoot? | 1900-01-22 | 1900-01-23 | 1 | Alex, Gilly, Nia, Larissa, Carter | bar: WEEK 5 W 23 to WEEK 5 R 24
6B. Location Mgrs run training for respective locations |  | 1900-01-22 | 1900-01-23 | 2 | bar: WEEK 5 W 23 to WEEK 5 R 24
C. Milestone: Device Location Rollout |  | 1900-01-22 | 1900-01-23 | bar: WEEK 5 W 23 to WEEK 5 R 24
1C. Project Plan Updates | How is everyone doing with the software? | 1900-01-25 | 1900-01-29 | 1 | Location Mgrs., Carter, Kitchen Staff, Deanna | bar: WEEK 6 M 26 to WEEK 6 F 30
2C Should one location be test pilot instead of all 3 at the same time? |  | 1900-01-22 | 1900-01-24 | 1 | bar: WEEK 5 W 23 to WEEK 5 F 25
3C. Finalize location rollout testing dates |  | 2023-02-01 | 2023-02-05 | 1 | Location Mgrs., Carter, Kitchen Staff, Deanna | bar: WEEK 7 M 1 to WEEK 7 F 5
4C. Run mock POS bar drill for any bugs | Mock launch | 2023-01-23 | 2023-01-25 | 1 day | Location Mgrs, Seyou, Peta, Kitchen Staff | bar: WEEK 5 W 23 to WEEK 5 F 25
5C. Soft launch test bar run through | Any kinks? Software bugs? | 2023-02-15 | 2023-02-17 | 2 days | Location Mgrs., Carter, Kitchen Staff, Deanna
6C. Determine later dates to swap out Upgraded devices with current one's |  |  |  | 7 days | bar: WEEK 5 W 23 to WEEK 5 R 24

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Tablet Device
Research software data for restaurant tablets | What brand works best for our POS? | 5 | 5 | 7 | 14 | H
Compare tablet pricing |  | 5 | 5 | 7 | 14 | H
Compatible OS system for current POS integration |  | 4 | 4 | 5 | 10 | M
Map out POS diagram for bar area in all locations | Make sure plugs are okay for proposed areas | 1 | 1 | 2 | 3 | H
Electrician installing bar tablets first | Will all devices be docked with a plug in? | 2 | 2 | 3 | 3 | H
Finalize new menu and coupons for content submission for tablets. | Carter will present and finalize with Omar, Deanna, Location Mgrs. | 14 | 7 | 7 | 14 | M
Submit coupon content for POS upload and testing. |  | 7 | 7 | 7 | 10 | H
Should POS be set for QR code access from customers phone as an alternative? |  | 1 | 1 | 1 | 2 | H
No tipping feature installed on POS - staff input/buyin | Be sure to attend each Location Mgrs staff meetings to ensure buy-in. | 1 | 1 | 1 | 2 | H
Drilldown 'no tipping' aspects on POS system |  | 1 | 1 | 1 | 2 | H
Test software on tablets | Does it integrate with current POS for ordering? | 1 | 1 | 1 | 2 | H
Approve tablet marketing wraps to match menu style/look | Does the tablet work with overall look? | 1 | 1 | 1 | 2 | H
Align and evaluate stakeholders |  | 1 | 1 | 1 | 2 | H
Milestone: Training and troubleshooting
Project Plan Updates |  | 1 | 1 | 1 | 2 | H
Locations hold small update project meeting about tablet launch |  | 1 | 1 | 1 | 2 | M
Create troubleshoot/support plan for all locations | What to do when things get crazy? | 2 | 2 | 3 | 4 | H
Create training modules for employees to learn | Easy to learn? | 2 | 2 | 3 | 4 | H
Train GM's on new software | Comfortable enough to troubleshoot? | 1 | 1 | 2 | 3 | M
Location Mgrs run training for respective locations |  | 2 | 3 | 2 | 3 | H
Milestone: Device Location Rollout
Project Plan Updates |  | 1 | 1 | 1 | 2 | H
Should one location be test pilot instead of all 3 at the same time? |  | 1 | 1 | 1 | 2 | M
Finalize location rollout testing dates |  | 1 | 1 | 2 | 2 | M
Run mock POS bar drill for any bugs |  | 1 | 1 | 2 | 3 | H
Soft launch test bar run through |  | 2 | 2 | 2 | 3 | M
Determine later dates to swap out Upgraded devices with current one's |  | 7 | 5 | 10 | 14 | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Everything about tableside POS ordering | https://pos.toasttab.com/blog/tableside-ordering | 2022-12-30 | Discusses pros/cons of tableside ordering thru device, QR code
What a POS rollout looks like | https://www.speedlinesolutions.com/blog/rollout-a-new-pos-to-your-restaurant-chain | 2022-12-30 | POS launch points and steps to consider

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5