## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
A. Milestone: Tablet Device
1A. Research software data for restaurant tablets | What brand works best for our POS? | 2022-12-27 | 2023-01-02 | 5 days | Seyou | bar: WEEK 1 M to WEEK 2 M
2A.Compare tablet pricing |  |  |  | 5
3A.Compatible OS system for current POS integration |  |  |  | 4
4A.Map out POS diagram for bar area in all locations | Make sure plugs are okay for proposed areas | 2023-01-12 | 2023-01-15 | 1 | Deanna, Seyou, Peta, Location Mgr.s | bar: WEEK 3 W to WEEK 4 M
5A.Electrician installing bar tablets first | Will all devices be docked with a plug in? | 2023-01-16 | 2023-01-19 | 2 | Seyou, Peta | bar: WEEK 4 M to WEEK 4 R
6A. Should POS be set for QR code access from customers phone as an alternative? | Should this be QR access only? | 2023-01-20 | 2023-01-24 | 1 | Deanna, Seyou, Peta, Location Mgr.s | bar: WEEK 4 F to WEEK 5 T
7A. No tipping feature installed on POS - staff input |  |  |  | 1
8A. Drilldown 'no tipping' aspects on POS system |  |  |  | 1
9A. Test software on tablets | Does it integrate with current POS for ordering? | 2023-01-20 | 2023-01-24 | 1 | Seyou, Peta, Location Mgrs. | bar: WEEK 4 F to WEEK 5 T
10A. Approve tablet marketing wraps to match menu style/look | Does the tablet work with overall look? | 2023-01-02 | 2023-01-06 | 1 | Deanna, Gilly, Alex, Peta
11A. Align and evaluate stakeholders | Confirm tablet look as wanted? | 2023-01-09 | 2023-01-11 | 1 | Omar, Deanna, Seyou, Peta | bar: WEEK 3 M to WEEK 3 W
B. Milestone: Training and troubleshooting
1B. Project Plan Updates |  |  |  | 1 | bar: WEEK 3 M to WEEK 3 W
2B. Locations hold small update project meeting about tablet launch |  |  |  | 1 | bar: WEEK 3 W to WEEK 4 M
3B. Create troubleshoot/support plan for all locations | What to do when things get crazy? | 2023-01-25 | 2023-01-27 | 2 | Seyou, Peta, Deanna, Location Mgrs. | bar: WEEK 5 W to WEEK 5 F
4B. Create training modules for employees to learn | Easy to learn? | 2023-01-25 | 2023-01-26 | 2 days | Kitchen Staff, Carter, Location Mgrs. | bar: WEEK 5 W to WEEK 5 R
5B. Train GM's on new software | Comfortable enough to troubleshoot? | 2023-01-25 | 2023-01-26 | 1 | Alex, Gilly, Nia, Larissa, Carter | bar: WEEK 5 W to WEEK 5 R
6B. Location Mgrs run training for respective locations |  |  |  | 2 | bar: WEEK 5 W to WEEK 5 R
C. Milestone: Device Location Rollout | bar: WEEK 5 W to WEEK 5 R
1C. Project Plan Updates | How is everyone doing with the software? | 2023-01-30 | 2023-02-03 | 1 | Location Mgrs., Carter, Kitchen Staff, Deanna | bar: WEEK 6 M to WEEK 6 F
2C Should one location be test pilot instead of all 3 at the same time? |  |  |  | 1 | bar: WEEK 5 W to WEEK 5 F
3C. Finalize location rollout testing dates |  | 2023-02-06 | 2023-02-10 | 1 | Location Mgrs., Carter, Kitchen Staff, Deanna | bar: WEEK 7 M to WEEK 7 F
4C. Run mock POS bar drill for any bugs | Mock launch | 2023-02-12 | 2023-02-12 | 1 day | Location Mgrs, Seyou, Peta, Kitchen Staff | bar: WEEK 5 W to WEEK 5 F
5C. Soft launch test bar run through | Any kinks? Software bugs? | 2023-02-15 | 2023-02-17 | 2 days | Location Mgrs., Carter, Kitchen Staff, Deanna | bar: WEEK 8 W to WEEK 8 F
6C. Determine later dates to swap out Upgraded devices with current one's |  |  |  | 7 days | bar: WEEK 5 W to WEEK 5 R

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Tablet Device
Research software data for restaurant tablets | What brand works best for our POS? | 5 | 5 | 7 | 14 | H
Compare tablet pricing |  | 5 | 5 | 7 | 14 | H
Compatible OS system for current POS integration |  | 4 | 4 | 5 | 10 | M
Map out POS diagram for bar area in all locations | Make sure plugs are okay for proposed areas | 1 | 1 | 2 | 3 | H
Electrician installing bar tablets first | Will all devices be docked with a plug in? | 2 | 2 | 3 | 3 | H
Finalize new menu and coupons for content submission for tablets. | Carter will present and finalize with Omar, Deanna, Location Mgrs. | 14 | 7 | 7 | 14 | M
Submit coupon content for POS upload and testing. |  | 7 | 7 | 7 | 10 | H
Should POS be set for QR code access from customers phone as an alternative? |  | 1 | 1 | 1 | 2 | H
No tipping feature installed on POS - staff input/buyin | Be sure to attend each Location Mgrs staff meetings to ensure buy-in. | 1 | 1 | 1 | 2 | H
Drilldown 'no tipping' aspects on POS system |  | 1 | 1 | 1 | 2 | H
Test software on tablets | Does it integrate with current POS for ordering? | 1 | 1 | 1 | 2 | H
Approve tablet marketing wraps to match menu style/look | Does the tablet work with overall look? | 1 | 1 | 1 | 2 | H
Align and evaluate stakeholders |  | 1 | 1 | 1 | 2 | H
Milestone: Training and troubleshooting
Project Plan Updates |  | 1 | 1 | 1 | 2 | H
Locations hold small update project meeting about tablet launch |  | 1 | 1 | 1 | 2 | M
Create troubleshoot/support plan for all locations | What to do when things get crazy? | 2 | 2 | 3 | 4 | H
Create training modules for employees to learn | Easy to learn? | 2 | 2 | 3 | 4 | H
Train GM's on new software | Comfortable enough to troubleshoot? | 1 | 1 | 2 | 3 | M
Location Mgrs run training for respective locations |  | 2 | 3 | 2 | 3 | H
Milestone: Device Location Rollout
Project Plan Updates |  | 1 | 1 | 1 | 2 | H
Should one location be test pilot instead of all 3 at the same time? |  | 1 | 1 | 1 | 2 | M
Finalize location rollout testing dates |  | 1 | 1 | 2 | 2 | M
Run mock POS bar drill for any bugs |  | 1 | 1 | 2 | 3 | H
Soft launch test bar run through |  | 2 | 2 | 2 | 3 | M
Determine later dates to swap out Upgraded devices with current one's |  | 7 | 5 | 10 | 14 | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Everything about tableside POS ordering | https://pos.toasttab.com/blog/tableside-ordering | 2022-12-30 | Discusses pros/cons of tableside ordering thru device, QR code
What a POS rollout looks like | https://www.speedlinesolutions.com/blog/rollout-a-new-pos-to-your-restaurant-chain | 2022-12-30 | POS launch points and steps to consider

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Productivity | Faster and more efficient experience | Are customers having better dining experience? | Baseline - 8min for appetizers/12-15min for entrees | FALSE
Functionality | Correct orders reaching kitchen | Is the customer entering the order correctly into tablet first? | What % of orders arrive correct? | FALSE
Functionality | Order accuracy/98% ticket accuracy | Were there unintended outcomes? | Metrics for total ticket orders. | FALSE
Safety | Any tablet issues? | Are tablets running correctly? Less than 5% weekly reports | What is the % of tech issues? | FALSE
Ease of use | Customer Self Checkout | Are customers able to checkout seamlessly? | Any charge issues etc? | FALSE
Effectiveness |  |  |  | FALSE
Functionality | Dining Experience | Anything different this time? | The experience has it changed for the positive or negative. | FALSE
Ease of use | Device | Did it change overall experience for positive/negative? | Interaction metrics - survey feedback | FALSE
Effectiveness | Marketing | Did they show to have value with the experience? | Did ticket totals increase due to device? | FALSE
Ease of use | Tablet Device | Do customers experience smoother checkout? | Less than 5% tablet technical issue complain in a week | FALSE
Functionality | Tablet Device | Do customers experience smoother checkout? | Tickets translate to kitchen correctly? | FALSE
Functionality | Tablet Device | Ticket total increase | 98% order accuracy in a month after launch | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Faster and more efficient experience | Are customers having better dining experience? | Baseline - 8min for appetizers/12-15min for entrees | Length of wait time? How long did you spend waiting on food after ordering? Did you feel rushed to hurry up and eat after food arrived? | Scaled
Correct orders reaching kitchen | Is the customer entering the order correctly into tablet first? | What % of orders arrive correct? | What was the accuracy of your food order? | Open-ended | open-ended
Order accuracy/98% ticket accuracy | Were there unintended outcomes? | Metrics for total ticket orders. | Did you interact with tablet outside of ordering? for Marketing | Open-ended | open-ended
Any tablet issues? | Are tablets running correctly? Less than 5% weekly reports | What is the % of tech issues? | Guest experience with the tablet: functionality, navigation, promotions, technical issues | Multiple choice | Functionality - easy? | Navigation - easy? | Promotion influenced adding to orders? yes/no | Tech issues? Yes/No
Customer Self Checkout | Are customers able to checkout seamlessly? | Any charge issues etc? | How was navigation when completing payment? | Open-ended | open-ended
Dining Experience | Anything different this time? | The experience has it changed for the positive or negative. | Was overall experience different from others? If brand new, what did you enjoy? Food, beverages, atmosphere, ease of interaction | Multiple choice | 1. very satisfied | 2. somewhat satisfied | 3. neither satisfied nor dissatisfied | 4. somewhat dissatisfied | 5. very dissatisfied
Device | Did it change overall experience for positive/negative? | Interaction metrics - survey feedback | Do patrons prefer tablet interaction over 100% server? | Scaled | Yes - so much easier | Neutral - Did not change experience? | No - I like the interaction
Marketing | Did they show to have value with the experience? | Did ticket totals increase due to device? | Did patrons use coupons/add-ons when ordering? Does ticket totals show the increase? | Scaled | Yes - good values | Neutral - fun to review | No - waste of data/time
Tablet Device | Do customers experience smoother checkout? | Less than 5% tablet technical issue complain in a week | Do you experience any issue when using the tablet? | Yes/No | Yes | No
Tablet Device | Do customers experience smoother checkout? | Tickets translate to kitchen correctly? | Could you tell us how is your experience when you use the tablet to place order? | Open-ended
Tablet Device | Ticket total increase | 98% order accuracy in a month after launch | Was it easy to order from the tablet menu? | Scaled | 1. Easy | 2. somewhat easy | 3. neutral/ok | 4. somewhat difficult | 5. very difficult