## Status Report
Project Name: Plant Pals Operations
Today's date: 14/12/22
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of Plant Pals to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action. |  |  |  | Amber
Completed Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Install new software | June 15 | Completed | IT Specialist |  | Took 3 days longer to finish
Began sending test batches of Plant Pals orders to customers | June 21 | Completed | Fulfillment Director |  | The number of orders exceeded targets by 15%.
Upcoming Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters on how to take care of their plants. | July 7 | Upcoming | Project Manager |  | The newsletter must follow Office Green’s brand design guidelines.
Hit 95% delivery dates | July 19 | Upcoming | Fulfillment Director |  | The error rate should be under 5%
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
The warehouse team reports that 10% of the plants were not properly potted. |  | Profit loss, complaints, and budget issues | Evaluate and adjust the plant potting process |  |  | Warehouse Operations Manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software |  |  | IT Specialist
Not enough delivery drivers to deliver all orders on time. |  | Cancelled Subscriptions | Hire and train more delivery drivers |  |  | HR Specialist